## Sheet1
TASK | DEADLINE | STATUS | COMMENTS
Order cameras, SD card readers, and DVRs | 2022-10-17 | NOT DONE
Finish data acquisition code | 2022-10-19 | IN PROGRESS | IMU and BARO work. GPS outputs data but need to parse it, have yet to get a genuine lock from GPS tho
Redesign avionics bay | 2022-10-22 | IN PROGRESS
Design and install blast shield | 2022-10-22 | NOT DONE
Install motor mounts | 2022-10-22 | NOT DONE
Assemble avionics bay | 2022-10-26 | NOT DONE
Install fins | 2022-10-26 | NOT DONE
Reprint first stage coupler (current one wobbles) | 2022-10-26 | NOT DONE
Reprint nose cone, add status LEDs | 2022-10-26 | NOT DONE
Figure out main parachute retention system | 2022-10-31 | NOT DONE
Program flight logic | 2022-10-31 | NOT DONE
Install parachute anchor | 2022-10-31 | NOT DONE
Install first stage coupler | 2022-10-31 | NOT DONE
Install avionics bay | 2022-11-02 | NOT DONE
Install first stage recovery system | 2022-11-05 | NOT DONE
Develop ground station software to receive flight telemetry | 2022-11-05 | NOT DONE