## Sheet1
TASK | DEADLINE | STATUS | COMMENTS
Order cameras, SD card readers, and DVRs | 2022-10-17 | DONE
Finish data acquisition code | 2022-10-19 | IN PROGRESS | IMU and BARO work. GPS outputs data but need to parse it, have yet to get a genuine lock from GPS tho
Redesign avionics bay | 2022-10-22 | IN PROGRESS | Everything should fit, need to double check once I get components. Accidentally modeled servo retention on wrong side of tube I think, gotta flip it
Design and install blast shield | 2022-10-22 | IN PROGRESS | Blast shield redesigned to two piece unit with wire passthrough. Need to CAD screwholes and then should be good to install
Install motor mounts | 2022-10-22 | IN PROGRESS | Printing new motor mount screwhole guide OCT 17
Install fins | 2022-10-26 | NOT DONE | Planning on printing new fin guide soon
Reprint first stage coupler (current one wobbles) | 2022-10-26 | DONE | Issue was due to motor mount screwholes interfering with coupler pegs. This has been fixed and current coupler design is acceptable.
Reprint nose cone, add status LEDs | 2022-10-26 | NOT DONE
Figure out main parachute retention system | 2022-10-31 | IN PROGRESS | Prototype designed and retaining servo integrated in avionics bay. Testing tbd
Program flight logic | 2022-10-31 | NOT DONE
Install parachute anchor | 2022-10-31 | NOT DONE
Install first stage coupler | 2022-10-31 | NOT DONE
Install first stage recovery system | 2022-11-05 | NOT DONE
Develop ground station software to receive flight telemetry | 2022-11-05 | NOT DONE
Assemble avionics bay | 2022-11-06 | NOT DONE | All the way back here since I'm waiting on components from China
Install avionics bay | 2022-11-12 | NOT DONE